## Consolidation
Task | Time in hours
Once user has signed into (app name) should have option to click on spotify button -create buttons and link button to spotify | 4
When user hits on spotify button, spotify API will bring them to the spotify login page - need to get api key for spotify | 2
If the user does not have an account, will have to click on spotifys new user option and create an account - happens within spotify | 2
If user is not interested in the service, or does not want to create a spotify account (interface) | 1
If user does have a spotify account will be asked to put in their spotify credtintials in order to log into the app | 3
Using the users inputs from the calendar, spotify will search database for playlist corresponding to the users activities (prob one activity at a time) - write code to look at specific spotify playlists and generes | 10
Next step: Use event titles from caleandar to search for playlists with related names | 20
Spotify will then return these playlists for the user to look through - code to return playlsits to user | 5
Optionally: display playlists on page | 20
The user will then have a choice to save those playlists to their personal spotify account to access later | 3
decide whether to log out of spotify or save credentials, return user back to homepage of website | 10
Total: | 80

## Karen
Task | Hours
Spotify OAUth | 5
Generate playlist button (front end) | 1
If not logged in to Google Calendar, prompt to log in | 3
Look up playlist relating to schedule | 15 | depending on how we implement it
Open spotify weblinks/spotify app with playlist | 5
Database with Spotify credentials to keep logged in | 15
Display calendar (front end) | 10
Log into app | 5
Keep app login credentials in database | 10
Create account for app | 10
Total | 79

## Yuheng
Task | Estimation
Spotify Login/Create account | 2
Use Spotify API to retrieve user information | 2
save user information to the user table | 1
create user interface for login (webpage) | 4
some kind of auth to access user info | 1
keep me logged in | 2
dynamically download user's spotify info to our user database | 3
save generated playlist to user's spotify account | 2
If user is not interested in the service, or does not want to create a spotify account (interface) | 1

## Leanna
Task | Time Estimation
Allow user to login to Spotify | 5
Google and Spotify OAuth | 5
Allow user to create new account | 2
Keep user logged in | 2
If user does not have a Spotify account, prompt them to create one | 2
Look at user's calendar and find playlists that relate to events | 8
Display playlists next to each event | 3
Allow user to save playlists in Spotify for later or listen to them | 5
If user does not want to create the needed accounts | 3

## Emily
Once user has signed into (app name) should have option to click on spotify button -create buttons and link button to spotify | 8 hrs
When user hits on spotify button, spotify API will bring them to the spotify login page - need to get api key for spotify | 6 hrs
If the user does not have an account, will have to click on spotifys new user option and create an account - happens within spotify or can make seperate button on website that directly takes user to new user sign in on spotify | 6 hrs
If user did not previously have an account will have to be redirected to login in page to login with their new account - api needs to recognize individual credinitals | 8 hrs
If user does have a spotify account will be asked to put in their spotify credtintials in order to log into the app | 6 hrs
Using the users inputs from the calendar, spotify will search database for playlist corresponding to the users activities (prob one activity at a time) - write code to look at specific spotify playlists and generes | 10 hrs
Spotify will then return these playlists for the user to look through - have code to return playlsits to user | 6 hrs
The user will then have a choice to save those playlists to their personal spotify account to access later | 4 hrs
Maybe have option where the user can also save playlist to website and display on the side to have easy access (might be possible bc spotify is free on computer) | 8 hrs
decide whether to log out of spotify or save credentials, return user back to homepage of website | 5 hrs